Project Planning Logic – Incident Lifecycle Automation in ServiceNow

# Planning Logic

Sprint: A fixed period in which the project team works to complete a selected set of stories.

Epic: A large functional requirement that is broken into smaller stories and delivered across one or more sprints.

Story: A small, independently trackable requirement describing value from a user's perspective.

Story Point: A relative estimate of effort and complexity. This project uses 1, 2, 3 and 5 points.

# Story Point Guidance

1 – Very easy

2 – Easy / small configuration

3 – Moderate workflow or validation

5 – Difficult / cross-module integration

# Sprint 1 – Incident Intake, Classification & Escalation

Incident Creation (USN-1) – 2

Incident Classification (USN-2) – 3

Knowledge Integration (USN-3) – 2

Assignment & Escalation (USN-4) – 3

Total Story Points in Sprint 1 = 2 + 3 + 2 + 3 = 10

# Sprint 2 – Change, Child Incident & Resolution

Emergency Change Integration (USN-5) – 5

Child Incident Creation (USN-6) – 3

Cause & Resolution Documentation (USN-7) – 3

Knowledge Article Creation (USN-8) – 3

Total Story Points in Sprint 2 = 5 + 3 + 3 + 3 = 14

# Sprint 3 – SLA Tracking & Final Validation

SLA and Related Record Tracking (USN-9) – 3

End-to-End Validation and Collaboration (USN-10) – 2

Total Story Points in Sprint 3 = 3 + 2 = 5

# Velocity Calculation

Total planned story points = 10 + 14 + 5 = 29.
Number of sprints = 3.
Average planned velocity = 29 / 3 = 9.67 story points per sprint.

# Burndown Logic

At the beginning of Sprint 1, 29 story points remain. Each completed story reduces remaining work. The ideal burndown is a steady decline toward zero by the end of Sprint 3. Actual progress can be tracked daily against the remaining story points.